## Table Sequence
Label | Table Title | Trigger within:
Table A | General Information | ALWAYS
Table B | Project Scope | ALWAYS
Table C | Compliance Results | ALWAYS
Table D | Exceptional Conditions | ALWAYS
Table E | Additional Remarks | ALWAYS
Table F | Design Review Kickoff Meeting | ALWAYS
Table G | Owner's Project Requirements (OPR) | Table B
Table H | Basis of Design (BOD) | Table B
Table I | Construction Document Design Review Checklist | ALWAYS
Table J | Commissioning Plan | Table B
Table K | Functional Performance Testing | Table B
Table L | Documentation and Training | Table B
Table M | Commissioning Report | Table B
Table N | Declaration of Required Certificates of Installation | ALWAYS
Table O | Declaration of Required Certificates of Acceptance | ALWAYS
- | Signature Page | ALWAYS

## Hyperlinks
Label | Hyperlink | Tables
§120.8 | http://www.energy.ca.gov/2015publications/CEC-400-2015-037/CEC-400-2015-037-CMF.pdf#page=159 | B, F, G, H, J, K, L, M
10-103(a)1 | http://www.energy.ca.gov/2015publications/CEC-400-2015-037/CEC-400-2015-037-CMF.pdf#page=18 | F
§120.5 | http://www.energy.ca.gov/2015publications/CEC-400-2015-037/CEC-400-2015-037-CMF.pdf#page=147 | K
§130.4 | http://www.energy.ca.gov/2015publications/CEC-400-2015-037/CEC-400-2015-037-CMF.pdf#page=177 | K
§140.9 | http://www.energy.ca.gov/2015publications/CEC-400-2015-037/CEC-400-2015-037-CMF.pdf#page=229 | K

## Headers
| User input | auto calculated | From another Table |  | From look up table
STATE OF CALIFORNIA
Nonresidential Building Commissioning
NRCC-CXR-E (Created XX/XX) |  |  |  | CALIFORNIA ENERGY COMMISSION
CERTIFICATE OF COMPLIANCE |  |  |  |  | NRCC-CXR
This document is used to demonstrate compliance with mandatory commissioning requirements in §120.8 for nonresidential buildings and hotel/motel or high-rise residential buildings with nonresidential spaces. This document does not demonstrate compliance with commissioning requirements within Title 24, Part 11, which need to be documented separately if they apply.
Project Name: |  |  |  | Report Page: | Page 1 of ??
Project Address: |  |  |  | Date Prepared:
Ben, this is a heading. The project name, address and date prepared should be a user input on the first page, but that should populate the heading on all other pages.
STATE OF CALIFORNIA
Nonresidential Building Commissioning
NRCC-CXR-E (Created XX/XX) |  |  |  | CALIFORNIA ENERGY COMMISSION
CERTIFICATE OF COMPLIANCE |  |  |  |  | NRCC-CXR-E
Project Name: |  |  |  | Report Page: | Page 1 of ??
Project Address: |  |  |  | Date Prepared:
Ben, please use the same footer as the LTI form.
First Page Heading
Heading all other pages

## A. General Info
|  | User input | auto calculated |  |  | From another Table |  | From look up table
A. GENERAL INFORMATION
01 | Project Location (city) |  |  | 04 | Building Size (ft2)
02 | Occupancy Type |  | see dropdown list below | 05 | Nonresidential Conditioned Floor Area (ft2) |  | see dropdown list below
03 | Project Type |  | see dropdown list below | 06 | HVAC System Type |  | see dropdown list below
STOP! Occupancy types that are not nonresidential, high-rise residential (> 4 stories), hotel/motel, or mixed-use and project types which are additions or alterations, are not required to comply with commissioning requirements in §120.8 and do not need to complete this compliance document.
STOP! Healthcare facilities are not required to comply with the Commissioning requirements in Part 6, but must comply with the applicable requirements in Chapter 7 of Title 24, Part 1 (OSHPD).
|  |  | Occupancy Type Dropdown |  |  |  | NR Conditioned Floor Area Dropdown
|  |  | Nonresidential |  |  |  | < 10,000 ft2
|  |  | High-rise Residential (> 4 stories) |  |  |  | 10,000 - 49,999 ft2
|  |  | Hotel/ Motel |  |  |  | 50,000 ft2 or greater
Mixed-Use
Healthcare Facility
|  |  | All other occupancy types | << triggers alert in Row 7
|  |  | Project Type Dropdown |  |  |  | HVAC System Type
|  |  | Newly constructed |  |  |  | Unitary or packaged equipment each serving one zone
|  |  | Major renovation |  |  |  | Two-pipe, heating only systems
|  |  | Core & shell only |  |  |  | All other HVAC system types (indicates "complex") | << indicates "complex"
Tenant fit out only
|  |  | Addition or Alteration | << triggers alert in Row 7
Table Tip:
Table A includes the "triggers" for the requirements in §120.8. Project details indicated on Table A will determine which requirements are shown on Table B. When calculating the nonresidential conditioned floor area for high-rise residential and hotel/motel occupancies, include all conditioned spaces which are not dwelling units or guest rooms.
Row 7 shows up if user selects "All other occupancy types" or "Addition or Alteration" Fill box with light red to make it really stand out.
Row 8 shows up if user selects "Healthcare Facility" from 02 dropdown
Note on E15: 2019 Update: Added Healthcare as a choice. If user selects this, trigger note in row 8.
Note on E21: Sally Blair: C&S or Tentant fit out only trigger note on row 10 in Table D tab.

## B. Project Scope
|  | User input |  | auto calculated | From another Table |  | From look up table
B. PROJECT SCOPE
Table Instructions: Based on project information provided in Table A, Table B indicates which commissioning related requirements apply per §120.8. Table B is not editable by the user.
Commissioning Requirements per §120.8
01 | Table F: Design Review Kickoff | §120.8(d)1 and §120.8(d)2 | The design review kickoff meeting establishes who will play the role of the design reviewer, the project schedule and identify owner's requirements. This meeting should be conducted during schematic design. |  |  | Never greyed out (ie, applies to all projects)
02 | Table G: Owner's Project Requirements (OPR) | §120.8(b) | The owner's project requirements establish the owner's goals, requirements, and expections for everything related to energy consumption and operation. This should be completed during schematic design. |  |  | Greyed out if <10,000 sqft and complex mechanical system is not indicated in Table A cells 05/06. If greyed out, replace the description in columns E-K with "This requirement does not apply." (italicized)
03 | Table H: Basis of Design (BOD) | §120.8(c) | The basis of design documents the design elements such as calculations and product selections that meet the owner's project requirements and applicable regulatory requirements. This should be completed during schematic design. |  |  | Greyed out if <10,000 sqft and complex mechanical system is not indicated in Table A cells 05/06. If greyed out, replace the description in columns E-K with "This requirement does not apply." (italicized)
04 | Table I: Design Review | §120.8(d) and §120.8(e) | The design reviewer(s) reviews the construction documents for clarity, completeness, and adherence to the owner's goals. Commissioning measures must be included in the construction documents to faciliate the design review and commissioning process. For projects with > 10,000 ft2 of nonresidential conditioned floor area, or with complex mechanical systems, the design review is for adherence with the Owner's Project Requirements (OPR) and Basis of Design (BOD). This should be conducted during design. |  |  | Never greyed out (ie, applies to all projects)
05 | Table J: Commissioning Plan | §120.8(f) | The commissioning plan is developed by the commissioning provider with input from the designer and defines the scope of commissioning the project. This should be drafted during design and completed during early construction. |  |  | Greyed out if <10,000 sqft and complex mechanical system is not indicated in Table A cells 05/06. If greyed out, replace the description in columns E-K with "This requirement does not apply." (italicized)
06 | Table K: Functional Performance Testing | §120.8(g) | Functional performance testing is conducted on building systems to demonstrate correct installation and operation. |  |  | Greyed out if <10,000 sqft and complex mechanical system is not indicated in Table A cells 05/06. If greyed out, replace the description in columns E-K with "This requirement does not apply." (italicized)
07 | Table L: Documentation and Training | §120.8(h) | Documentation of the operational aspects of the building shall be completed within the Systems Manual and delivered to the building owner or representative and facilities operator. |  |  | Greyed out if <10,000 sqft and complex mechanical system is not indicated in Table A cells 05/06. If greyed out, replace the description in columns E-K with "This requirement does not apply." (italicized)
08 | Table M: Commissioning Report | §120.8(i) | A complete report of commissioning process activities undertaken through the design, construction and reporting recommendations for post-construction phases of the building project shall be completed and provided to the owner or representative. |  |  | Greyed out if <10,000 sqft and complex mechanical system is not indicated in Table A cells 05/06. If greyed out, replace the description in columns E-K with "This requirement does not apply." (italicized)
Table Tip:
Table B will indicate applicable requirements from Part 6, §120.8 based on the project details completed in Table A. of the form. Any tables that are not identified as "not applicable" will need to be completed for permit application. Table B is not editable by the user.

## C. Compliance
|  | User input |  |  | auto calculated |  |  | From another Table |  |  | From look up table
C. COMPLIANCE RESULTS
Table Instructions: Table C will indicate if the project data input into the compliance document is compliant with commissioning requirements per §120.8. This table is not editable by the user. If this table says "DOES NOT COMPLY" or "COMPLIES with Exceptional Conditions" refer to Table D. for guidance.
01 |  | 02 | 03 |  | 04 | 05 | 06 | 07 | 08 | 09
Design Review Kickoff |  | Owners Project Requirements | Basis of Design |  | Design Review | Commissioining Plan | Functional Performance Testing | Documentation and Training | Commissioning Report | Compliance Results
Table F |  | Table G | Table H |  | Table I | Table J | Table K | Table L | Table M
YES |  |  |  |  | NO |  |  |  |  | COMPLIES or DOES NOT COMPLY
10 | Design Reviewer(s) for the project include: |  |  | bring in names from Table F 04 | [5 empty] | COMPLIES or DOES NOT COMPLY
Tool Tip:
Note on A9: Sally Blair: Says "YES" if Table F 03 is checked "YES" AND date of design review is not blank in 01 AND either altert in Row 31 pops up or 10-20 are completed. Otherwise says "No".
Note on C9: Sally Blair: Says "YES" if Table G 01 is checked "YES" & 02 is completed OR if Table G 01 is checked "No"and 03-51 are completed. Otherwise says "No"
Note on E9: Sally Blair: Says "Yes" if Table H 01 is checked "Yes" and 02 is completed OR if Table H 01 is checked "No"and 03-34 are completed. Otherwise says "No"
Note on G9: Sally Blair: Says "Yes" if Table I 01 is checked "YES" OR if I 01 is checked "No" and 02-09 are completed. Otherwise, says "No"
Note on I9: Sally Blair: Says "YES" if Table J 01 is checked "Yes" and 02 is completed OR if Table J 01 is checked "No" and 03-14 are completed. Otherwise says "No"
Note on J9: Sally Blair: Columns 02/03/05/06/07/08 grey out or open based on Table B. Says "Yes" if 01 is checked. Othwerwise says "No"
Note on K9: Sally Blair: Says "Yes" if 01 and 02 are checked. Othwerwise says "No"
Note on L9: Sally Blair: Says "Yes" if 01 is checked Otherwise says "No"
Note on M9: Sally Blair: Says "COMPLIES" if all columns which are not greyed out say "YES". Otherwise, says "DOES NOT COMPLY"
Note on M10: Sally Blair: Says "COMPLIES" if Table F column 3 is clicked, Otherwise, says "DOES NOT COMPLY".

## D. Exceptional Conditions
| User input | auto calculated | From another Table | From look up table
D. EXCEPTIONAL CONDITIONS
This table is auto-filled with uneditable comments because of selections made or data entered in tables throughout the form.
Comment
Ben, if "Core & Shell only" or "Tenant Fit Out only" have been selected on Table A 03, the following note should appear: "Either Core and Shell or Tenant fit out has been indicated in Table A. Please note commissioning may be completed for the entire building prior to tenant improvements, or for each individual tenant improvement. The local enforcement agency may have commissioning policies for multi-tenant buildings."
Ben, if "Yes" is selectedin Table G. indicating that the OPR is attached, trigger this note "Table G. indicates that the Owner's Project Requirements (OPR) document is attached to the permit application."
Ben, if "Yes" is selected in Table H. indicating that the BOD is attached, trigger this note "Table H. indicates that the Basis of Design (BOD) document is attached to the permit application."
Ben, if "Yes" is selected in Table I. indicating that the Design Review is attached, trigger this note "Table I. indicates that a Design Review document is attached to the permit application."
Ben, if "Yes" is selected in Table J. indicating that the Cx Plan is attached, trigger this note "Table J. indicates that a draft commissioning plan is attached to the permit application."
Table Tip:
Table D is auto-filled with warnings and compliance notes directed to the form user and the enforcement agency based on data inputs and calculations in the rest of the NRCC-CXR. It may not be directly edited by the form user.
Note on B10: Sally Blair: CEC, this language is adapted from Blueprint #107

## E. Additional Remarks
| User input | auto calculated | From another Table | From look up table
E. ADDITIONAL REMARKS
This table includes remarks made by the permit applicant to the Authority Having Jurisdiction.
Table Tip:
Table E allows user input of additional information to support the compliance documentation.

## F. Design Review Kickoff
|  | User input |  |  | auto calculated |  |  | From another Table |  |  | From look up table
F. DESIGN REVIEW KICKOFF MEETING
Table Instructions: Complete this table to indicate that the design reviewer meets the qualification requirements per Title 24, Part 1 Section 10-103(a)1 and to demonstrate compliance with design review kickoff requirements per §120.8(d)2. This meeting should occur during the Schematic Design phase of the project.
Design Review Kickoff Meeting Details
01 | Date of Design Review Kickoff Meeting
02 | Meeting Attendees: (one person may play multiple roles)
¨ | Owner/ Facility Manager:_________________________________ |  |  |  | ¨ | Design Reviewer(s): _________________________________
¨ | Project Manager: _________________________________ |  |  |  | ¨ | Design Architect/ Engineer(s):_______________________
¨ | Contractor: ______________________________________ |  |  |  | ¨ | Certified Acceptance Test Tech(s): _____________________
¨ | Commissioning Provider: _____________________________ |  |  |  | ¨ | Energy/ T24 Part 6 Consultant: _____________________
Design Reviewer Qualifications per Title 24, Part 1 Section 10-103(a)1
The design reviewer(s) must be licensed professional engineers or licensed architects, or licensed contractors representing services performed by or under the direct supervision of a licensed engineer or architect, as specified in the provisions of Division 3 of the Business and Professions Code. | [7 empty] | Do the Design Reviewer(s) meet these qualifications?
03 | In addition, for buildings with < 10,000 ft2, the design reviewer(s) may be the engineer or architect of record. The design reviewer(s) may also be a qualified in-house engineer or architect with no other project involvement or a third party engineer, architect or contractor. | [6 empty] | YES | NO
<< only open this box for user entry if <10,000 sf is indicated on Table A 05. Otherwise, minimize so not visible.
[8 empty] | m | ●
03 | In addition, for buildings with > 10,000 ft2 but < 50,000 ft2, the design reviewer(s) shall be a qualified in-house engineer or architect with no other project involvement or a third party engineer, architect, or contractor. | [6 empty] | YES | NO
<< only open this box for user entry if 10,000 - 49,999 sf is indicated on Table A 05. Otherwise, minimize so not visible.
[8 empty] | m | ●
03 | In addition, for buildings with > 50,000 ft2, or complex mechanical systems1, the design reviewer(s) shall be a third party design engineer, architect, or contractor. | [6 empty] | YES | NO
<< only open this box for user entry if 50,000 sf or greater is indicated on Table A 05 OR if All Other HVAC Types is selected on Table A 06. Otherwise, minimize so not visible.
[8 empty] | m | ●
04 | The design reviewer(s) for this project will be:
1 FOOTNOTE: Complex Mechanical Systems are systems that include 1) fan systems each serving multiple thermostatically controlled zones, or 2) built-up air handler systems (non-unitary or nonpackaged HVAC equipment), or 3) hydronic or steam heating systems, or 4) hydronic cooling systems.
Preliminary Construction Schedule
|  |  |  | Start Date |  |  | Completion Date
05 | Schematic Design |  |  | yyyy-mm-dd |  |  | yyyy-mm-dd
06 | Design Development |  |  | yyyy-mm-dd |  |  | yyyy-mm-dd
07 | Construction Documents |  |  | yyyy-mm-dd |  |  | yyyy-mm-dd
08 | Construction |  |  | yyyy-mm-dd |  |  | yyyy-mm-dd
09 | Building Turnover |  |  | yyyy-mm-dd |  |  | yyyy-mm-dd
Please proceed to Table G. to complete an Owners Project Requirements (OPR) Document per §120.8(b). | [9 empty] | << This pops up for buildings > 10,000 sf as indicated in Table A05
Project Goals Related to Energy Efficiency | [9 empty] | << This, and everything below it, pops up for buildings < 10,000 sf as indicated in Table A05
10 | Operational Costs |  | Describe the broad goals relative to operational costs.
11 | Desired Building Lifespan |  | Describe the desired building lifespan.
12 | Equipment Lifecycle |  | Describe the broad goals relative to the lifecycle of building systems equipment. | [6 empty] | << Ben, all of the language in italics here should appear when the table expands, but go away when the user starts to type something in the box.
13 | Project Energy Efficiency Goals |  | Describe the project energy efficiency goals, such as Energy Use Intensity (EUI) in kBtu/ft2.
14 | Envelope Goals |  | Describe any efficiency goals related to the building's roof, walls, windows or floors.
15 | HVAC System Goals |  | Describe heating and cooling requirements and any special considerations. Describe the anticpated occupancy schedule and if users will have the ability to override the HVAC setpoints during unoccupied periods. Describe desired occupant control capabilities. Describe any other special considerations that should be reviewed during the commissioning design review.
16 | Indoor Lighting System Goals |  | Describe any efficiency goals related to the building's indoor lighting systems.
17 | Outdoor Lighting System Goals |  | Describe any efficiency goals related to the building's indoor lighting systems.
18 | Water Heating System Goals |  | Describe any efficiency goals related to the building's water heating system.
19 | Equipment and System Specifications |  | Describe the desired equipment type, quality and reliability requirements, preferred manufacturers, and energy efficiency targets.
20 | Operations and Maintenance |  | Describe the desired level of training and orientation for building occupants to understand use building systems, and the level of training and orientation of operations and maintenance staff to understand and maintain the building systems.
Table Tips
During the schematic design phase of the project, the project team should meet to discuss the project scope, schedule, and team coordination related to building commissioning. The design reviewer(s) should be designated at this time to ensure required qualifications are met. If the Commissioning Provider is acting as the design reviewer, they should be present at this meeting. The design review kickoff would be an appropriate time to discuss and document the owners project requirements. Owner's project requirements should include energy efficiency measures that are required to comply with Title 24, Part 6.
Note on L15: Rebecca Rice: Ben - whichever of these 3 boxes remains editable MUST say yes for Table C to show compliance. If no, then Table C column 01 should say NO and Table C should show Does not comply
Note on A23: Rebecca Rice: Footnote only triggered if 'In addition, for buildings with >= 50,000 or complex…" is checked.

## G. OPR
|  | User input | auto calculated | From another Table | From look up table
G. OWNER'S PROJECT REQUIREMENTS (OPR)
Table Instructions: Complete the table below if not attaching an OPR document, or attach an OPR document to your permit application to demonstrate compliance with §120.8(b). If a specific field is not applicable to the project scope, put "NA". Per §120.8(b), the OPR is to be completed before design begins. This may be done at the Design Review Kickoff Meeting (see Table F.).
01 | Attaching Completed Owner's Project Requirements Document? | YES | NO
|  | m | ●
02 | Owners Project Requirements Document Authors and Roles
Energy Efficiency Goals: General
03 | What is the target total energy usage per square foot per year? (ie, Energy Use Intensity (EUI) in kBtu/ft2) | Enter the energy use intensity target to meet owner's goals in kBtu/ft2
04 | What is the target total energy cost per square foot per year? | Enter the energy cost target to meet owner's goals in $/ ft2/yr
05 | Is kW demand control specifically an interest of the client or the design team? If so, for what reason? | Discuss whether kW demand control is desired on the project.
06 | What are the project goals and requirements for building siting that will impact energy use? | Discuss the implications of siting constraints on energy use.
07 | What are the project goals and requirements for landscape that will impact energy use? | Discuss the implications of landscaping design decisions on energy use.
08 | Additional notes regarding general efficiency. | Describe any additional discussions or goals around general energy efficiency.
Energy Efficiency Goals: Envelope
09 | What are the project goals and requirements for building fenestration that will impact energy use? | Describe the implications of fenestration decisions on energy use and Part 6 compliance.
10 | What are the project goals and requirements for walls/floors that will impact energy use? | Describe the implications of wall/floor details on energy use and Part 6 compliance.
11 | What are the project goals and requirements for building roof that will impact energy use? | Describe the implications of roof details on energy use and Part 6 compliance.
12 | Additional notes regarding envelope efficiency. | Describe any additional discussions or goals around envelope energy efficiency.
Energy Efficiency Goals: HVAC Systems
13 | List the HVAC system types considered desirable, and ones that are not to be considered. | Describe any HVAC system constraints or preferences.
14 | What is the desired thermostatic setpoint range in the heating season, and cooling season? | Discuss and document desired thermostat setpoints.
15 | What is the expected occupancy schedule? Will the occupants be allowed to override the mechanical system controls during “unoccupied hours?” | Discuss and document design considerations.
16 | Are there times during the day that the zone temperature is allowed to drift out of the temperature setpoint range? If so, how long and what times are acceptable. | Discuss and document design considerations.
17 | Is it acceptable to let the facility cool down to a night setback temperature in the winter? | Discuss and document design considerations.
18 | Is it acceptable to let the facility temperature drift above setpoint during the summer evenings? | Discuss and document design considerations.
19 | How many days out of the year is it acceptable to not meet the entire cooling/heating load? | Discuss and document load calculation considerations.
20 | Are there zones with special temperature, humidity, air filtering, etc., requirements? If so, identify and list the special environmental control requirements. | Discuss and document spaces with special environmental control requirements.
21 | What expectations are there around building ventilation? | Discuss and document design considerations for ventilation.
22 | Is occupancy-based demand control ventilation (DCV) desired, or required? | Discuss and document design considerations for DCV.
23 | Is a building automation system (BAS) desired? If so, what are the requirements of the BAS and what value is expected to be added with the BAS? | Describe the owner's goals related to having a BAS.
24 | Will zone setpoints be controlled locally by the user, or via the BAS only by the maintenance staff? | Describe how occupants should be interacting with controls to meet owner's requirements.
25 | Explain the requirements of the HVAC system in regards to temperature, humidity and draft control. | Describe controls design decisions to meet owner's requirements.
26 | Explain the requirements of the facility with regard to indoor air quality. | Describe IAQ design decisions to meet owner's requirements.
27 | What are the acoustic requirements of the HVAC system within the various spaces of the facility? | Discuss and document acoustic requirements applicable to the spaces in the project.
28 | Describe the maintenance plan and how the HVAC design needs to address operation and maintenance issues. | Describe operation and maintenance goals & related design decisions.
29 | Additional notes regarding HVAC system efficiency. | Describe any additional discussions or goals around HVAC energy efficiency.
Energy Efficiency Goals: Indoor Lighting Systems
30 | Describe specific lighting requirements including quality and glare. | Describe design considerations for the lighting system to meet owner goals.
31 | List the desired types of lighting (if any) and ones that are not to be considered. (example: fluorescent in 2x2 grid, accent lighting, particular lamps) | Describe owner preferences related to lighting system components.
32 | Describe (if any) task lighting requirements. | Describe any design considerations related to task lighting.
33 | Describe any desired features of the lighting control system including occupancy, daylighting, and demand response if applicable. | Describe design considerations for the lighting control system.
34 | What is the expected occupancy schedule? Will the occupants be allowed to override the lighting system controls during “unoccupied hours”? | Discuss and document the desired interaction with overriding indoor lighting control systems.
35 | Does occupancy-based control need to be coordinated with mechanical demand control ventilation? | Discuss if occupancy based controls need to be coordinated with DCV to meet owner's goals.
36 | Describe how occupants will interact with the lighting control system (overrides etc.) | Discuss and document the occupant's desired interaction with indoor lighting control systems.
37 | Additional notes regarding Indoor Lighting system efficiency. | Describe any additional discussions or goals around indoor lighting system energy efficiency.
Energy Efficiency Goals: Outdoor Lighting Systems
38 | Describe specific outdoor lighting requirements. | Describe design considerations for the outdoor lighting system to meet owner goals.
39 | List the desired types of outdoor lighting, including lighting for building façade, landscape, walkways, roof-top, etc. if applicable. | Describe owner preferences related to outdoor lighting system components.
40 | Describe any features of the outdoor lighting control system, including motion sensors, photocontrol, time-switch and automatic scheduling. | Describe design considerations for the lighting control system.
41 | Describe how occupants will interact with the lighting control system (overrides etc.) | Discuss and document the occupant's desired interaction with outdoor lighting control systems.
42 | Additional notes regarding Outdoor lighting system efficiency. | Describe any additional discussions or goals around outdoor lighting system energy efficiency.
Energy Efficiency Goals: Water Heating Systems
43 | Describe what the water heating system will be used for and expected demand? | Describe owner goals and preferences related to the water heating system.
44 | Describe the desired type (if any) of water heating system and those that should not be considered. (example: instantaneous, heatpump, manufacturer, etc.) | Describe owner preferences related to water heating system components.
45 | What are the desired automation features and controls for the water heating system. | Describe owner preferences related to water heating system controls.
46 | What are the efficiency requirements of the water heating system? | Describe owner requirements related to water heating system efficiency.
47 | Additional notes regarding Water Heating system efficiency. | Describe any additional discussions or goals around water heating system energy efficiency.
Operation and Maintenance Requirements
48 | Desired building lifespan | Describe if there are any owner's goals related to the building lifespan.
49 | What are the broad goals relative to life cycle of the equipment? | Describe any owner's goals related to equipment lifespan.
50 | What is the desired level of training and orientation for building occupants to understand and use the building systems? | Describe any owner's goals related to operation and training for building occupants.
51 | What is the desired level of training and orientation for O&M staff to understand and maintain the building systems? | Describe any owner's goals related to operation and training for building facility managers.
Table Tip:
It is recommended that the OPR be completed at the Design Review Kickoff in the early design stages of the project. Someone knowledgeable about the building's desired operation should be present to discuss and document these requirements with the team. The Commissioning Provider should also be present as early as possible to facilitate the commissioning process.
Remove Last
Add System
Note on C7: Sally Blair: If users selects "Yes", trigger note on Row 11 in Table D.
Note on F7: Sally Blair: If user selects "No", "Energy Efficiency Goals: General" row, and everything below it expands for user input.
Note on C10: Sally Blair: Ben, let's restrict this to a number entry
Note on C11: Sally Blair: Ben, let's restrict this to a number entry
Note on I16: Sally Blair: Ben, I deleted the "Add Row" and "Remove Last" for each of these sections & added this "Additional Notes" area for the general EE section per a suggestion from Diane.
Note on D71: Rebecca Rice: The 'Add System' button will duplicate the "heading Row" for the section (the one which includes "Operation and Maintenance Requirements" and add one row under it. This will be used if user wants to add a new system type such as "Energy Efficiency Goals: Irrigation System, etc."
Note on I71: Sally Blair: Ben, this Add System & Remove last button I want to keep. The add row can go away. The remove last should remove the system then, instead of just the row.

## H. BOD
H. BASIS OF DESIGN (BOD)
Table Instructions: Complete the table below if not attaching a BOD document, or attach a BOD document to demonstrate compliance with §120.8(c). If a specific field is not applicable to the project scope, put "NA". Per §120.8(c), the BOD should be completed and updated during the design phase.
01 | Attaching Completed Basis of Design Document? | YES |  | NO
|  | m |  | ●
02 | Basis of Design Document Authors and Roles
Title 24 Part 6 Compliance Approach
03 | Title 24, Part 6 Compliance Approach (select one): | ¨ Prescriptive | ¨ Performance | ¨ Both (Prescriptive and Performance)
04 | If both, describe prescriptive scopes and performance scopes: | Insert a description of which scopes are using prescriptive vs. which are using performance.
General Energy Efficiency Goals
05 | Energy Use Intensity (EUI) | Insert a description of how the design's energy use intensity (EUI) will be calculated.
06 | Energy Cost Budget | Insert a description of how the design's energy cost per square foot will be calculated.
Envelope Basis of Design
07 | Window to Wall Ratio | Insert a description of the target design window to wall ratio.
08 | Opaque Wall Assembly | Insert a description of the wall assemblies and energy efficiency features/strategies.
09 | Window Performance | Insert a description of the target design window performance including U Values, Glazing, and Solar Heat Gain Coefficient for all window types.
10 | Response to OPR Document | Provide reasons why the envelope design is the best choice to meet Owner's Project Requirements outlined in the OPR Document (See Table G.)
HVAC System Basis of Design
11 | HVAC System Design | Insert general HVAC system description
12 | Heating System Description | Insert system type(s), location, control type, efficiency features, outdoor air ventilation strategy, indoor air quality features, noise reduction features, environmental benefits, other special features
13 | Cooling System Description | Insert system type(s), location, control type, efficiency features, outdoor air ventilation strategy, indoor air quality features, noise reduction features, environmental benefits, other special features
14 | Ventilation System Description | Insert system type(s), location, control type, efficiency features, ventilation strategies, indoor air quality features, noise reduction features, environmental benefits, other special features
15 | Control Intent Narrative/ Sequence of Operations | Provide operating schedules, set points, etc. if known at time of design. May refer to plans and/or specifications if sequence of operations is included there. If these specifics aren't available, provide a control intent narrative that outlines the intent of the control system.
16 | Outside Air Supply | Provide narrative of how all spaces and zones meet the outside air ventilation requirements in the OPR Document
17 | Load Calculations | Describe the load calculation methodology used to meet requirements in the OPR document
18 | Indoor Design Conditions |  | Occupied Spaces | Unoccupied Spaces
|  | Occupied Periods | Temp (oF) | Temp (oF) | Relative Humidity (%)
|  | Heating | 00 | 00 | 00
|  | Cooling | 00 | 00 | 00
|  | Unoccupied Periods | Temp (oF) | Temp (oF) | Relative Humidity (%)
|  | Heating | 00 | 00 | 00
|  | Cooling | 00 | 00 | 00
19 | Response to OPR Document | Provide reasons why the selected system is the best choice to meet Owner's Project Requirements outlined in the OPR Document (See Table G.)
Indoor Lighting System Basis of Design
20 | Indoor Lighting System Narrative | Generally describe the indoor lighting system which will be commissioned
21 | Fixture Types | Insert specific fixture types
22 | Lamp and Ballast Types | Insert specific lamp and ballast types
23 | Control Types | Describe control types and areas to be controlled
24 | Control Intent Narrative/ Sequence of Operations | Provide operating schedules, set points, etc. if known at time of design. May refer to plans and/or specifications if sequence of operations is included there. If these specifics aren't available, provide a control intent narrative that outlines the intent of the control system.
25 | Response to OPR Document | Provide reasons why the selected system is the best choice to meet Owner's Project Requirements outlined in the OPR Document (See Table G.)
Outdoor Lighting System Basis of Design
26 | Outdoor Lighting System Narrative | Generally describe the outdoor lighting system which will be commissioned
27 | Fixture Types | Insert specific fixture types
28 | Lamp and Ballast Types | Insert specific lamp and ballast types
29 | Control Types | Describe control types and areas to be controlled
30 | Control Intent Narrative/ Sequence of Operations | Provide operating schedules, set points, etc. if known at time of design. May refer to plans and/or specifications if sequence of operations is included there. If these specifics aren't available, provide a control intent narrative that outlines the intent of the control system.
31 | Response to OPR Document | Provide reasons why the selected system is the best choice to meet Owner's Project Requirements outlined in the OPR Document (See Table G.)
Water Heating System Basis of Design
32 | Water Heating System Narrative | Generally describe the water heating system which will be commissioned
33 | Water Heating Load Calculations | Describe sizing calculation method, assumptions, and results
34 | Response to OPR Document | Provide reasons why the selected system is the best choice to meet Owner's Project Requirements outlined in the OPR Document (See Table G.)
Remove Last
Table Tip:
The Basis of Design table should be completed early in design to indicate how initial design decisions are supporting owner's requirements and goals outlined in the Owner's Project Requirements (OPR) document. The design team typically completes the Basis of Design.
Add System
Note on H5: Sally Blair: If users selects "Yes", trigger note on Row 12 in Table D.
Note on J5: Sally Blair: If user selects "No", "Title 24 Part 6 Compliance Approach" row, and everything below it expands for user input.
Note on A56: Rebecca Rice: 'Add System' button will duplicate the 'Heading' row and one row under it. All fields are user entry.
Note on J56: Sally Blair: Ben, this Add System & Remove last button I want to keep. The add row can go away. The remove last should remove the system then, instead of just the row.

## I. Design Review
I. CONSTRUCTION DOCUMENT DESIGN REVIEW CHECKLIST
Table Instructions: The design reviewer(s) may fill out the table below or attach a design review document that lists the items checked by the design reviewer(s) during the construction document review. For buildings with > 10,000 ft2 conditioned floor area, the design review will ensure the construction documents meet the Owner's Project Requirements (Table G.) and the Basis of Design Documents (Table H.). For buildings with < 10,000ft2 conditioned floor area, the design review will ensure the construction documents meet the goals documented in Table F. during the Design Review Kickoff.
01 | Attaching Completed Design Review Documentation? |  | YES | NO
|  |  | m | ●
Design Review Checklist
02 | Envelope Design | Describe how the envelope design reflected in the contract documents meets each owner requirement documented in the OPR/ BOD or Table F. Describe any issues that were identified and the resolution.
03 | HVAC System Design | Describe how the HVAC system design reflected in the contract documents meets each owner requirement documented in the OPR/ BOD or Table F. Describe any issues that were identified and the resolution.
04 | HVAC Controls Design | Describe how the HVAC controls design reflected in the contract documents meets each owner requirement documented in the OPR/ BOD or Table F. Describe any issues that were identified and the resolution.
05 | Indoor Lighting System Design | Describe how the indoor lighting system design reflected in the contract documents meets each owner requirement documented in the OPR/ BOD or Table F. Describe any issues that were identified and the resolution.
06 | Indoor Lighting Controls Design | Describe how the indoor lighting controls design reflected in the contract documents meets each owner requirement documented in the OPR/ BOD or Table F. Describe any issues that were identified and the resolution.
07 | Outdoor Lighting System and Controls Design | Describe how the outdoor lighting controls design reflected in the contract documents meets each owner requirement documented in the OPR/ BOD or Table F. Describe any issues that were identified and the resolution.
08 | Water Heating System Design | Describe how the water heating system design reflected in the contract documents meets each owner requirement documented in the OPR/ BOD or Table F. Describe any issues that were identified and the resolution.
09 | Other Systems and Features | Describe how any other systems or features reflected in the contract documents meets owner requirements documented in the OPR/ BOD or Table F. Describe any issues that were identified and the resolution.
Table Tip:
The design review should be conducted to ensure the construction documents include design features that meet the owner's project goals and requirements. This should include energy efficiency measures and strategies that are necessary to comply with Title 24, Part 6. The design reviewer(s) may need to coordinate with designers or the Title 24, Part 6 consultant to complete the design review.
Note on I5: Sally Blair: If users selects "Yes", trigger note on Row 13 in Table D.
Note on K5: Sally Blair: If the user selects "No", the "Design Review Checklist" row, and everything below it expands for user input.

## J. Commissioing Pln
J. COMMISSIONING PLAN
Table Instructions: Complete the table below if not attaching a Commissioning Plan document, or attach a Commissioning Plan document to demonstrate compliance with §120.8(f). Per §120.8(f), the Commissioning Plan is to be started during the design phase and a completed draft must be submitted with permit application.
01 | Attaching Completed Commissioning Plan? |  |  |  | YES | NO
[5 empty] | m | ●
02 | Commissioning Plan Authors and Roles
Commissioning Provider Information
03 | Company Name |  | 05 | Contact Email
04 | Contact Person |  | 06 | Contact Phone
Commissioning Process Overview
07 | Owner Goals | Describe the goals for the commissioning process including but not limited to meeting code requirements, meeting OPR and BOD requirements.
08 | Roles and Responsibilities | Describe the roles and responsibilities of the commissioning provider, owner/owners representative, design team, construction manager, certified Acceptance Test Technician, mechanical, electrical, and controls contractors, testing and balancing contractor, equipment suppliers, and building inspector.
09 | Schedule | Describe how the commissioning and acceptance testing process will fit into the construction schedule.
Commissioning Activities During Construction
10 | Construction Observation | Describe when jobsite observations will be conducted and the intent of these observations.
11 | Issues Logs | Describe how issues logs will be used and the project team members these will be submitted to for recertification.
12 | Installation Verification | Describe the installation verification processes and responsible parties.
13 | Functional Performance Testing | Describe how the Commissioning Provider, Acceptance Test Technician and Subcontractor will interact during tests listed in Table K. Functional Performance Testing.
14 | Documentation and Training | Describe the review of the operation manuals and how the commissioning provider will facilitate the training of owner and applicable maintenance staff on the building systems.
Table Tips
The commissioning plan is developed by the commissioning provider with input from the designer and defines the scope and the budget of the commissioning project.
Note on H5: Sally Blair: If users selects "Yes", trigger note on Row 14 in Table D.
Note on J5: Sally Blair: If user selects "No", "Commissioning Provider Information" row, and everything below it expands for user input.

## K.FPT
K. FUNCTIONAL PERFORMANCE TESTING
Table Instructions: Complete the table below to demonstrate compliance with functional performance testing requirements per §120.8(g).
By checking this box, the responsible party1 certifies that functional performance testing will be executed to demonstrate the correct installation and operation of each component, system and system-to-system interface in accordance with the acceptance test requirements in §120.5, §130.4 and §140.9. The functional performance testing reports shall contain information addressing each of the building components tested, the testing methods utilized, and include any readings and adjustments made. |  |  |  | 01
¨
The following acceptance tests have been identified as applicable to the project scope:2
02 | 03 | 04 |  | 05
System/ Equipment to be Tested | Brief description of functional performance test | Applicable Reference Appendix |  | Certified Acceptance Test Technician Required?
|  | See dropdown list |  | "Yes" if lighting AT, "No" if MCH or ENV
|  |  | Add Row | Remove Last
The acceptance tests required by Title 24, Part 6 outline the minimum functional performance testing scope to be conducted for compliance. However, the commissioning scope may include additional functional performance tests on systems or equipment not having acceptance tests required by Title 24, Part 6.
The following additional functional performance tests have been requested by the owner or owner's representative:
06 | 07
System/ Equipment to be Tested | Brief description of functional performance test
|  |  | Add Row | Remove Last
1 FOOTNOTE: See the signature block on the last page of this compliance document for the responsible party.
2 Required acceptance tests can be determined by reviewing the "Certificates of Acceptance" table on each Certificate of Compliance submitted for permit application.
Applicable Reference Appendix Dropdown
Table Tip: |  | NA7.4.1- Fenestration |  | No
Acceptance tests applicable to the project scope are indicated on the other prescriptive NRCC forms, or triggers can be found in §120.5, §130.4 and §140.9 of the Standards. Indicate which acceptance tests are applicable to the project scope, and any additional functional performance testing that is required to meet owner's requirements. |  | NA7.4.2- Window Films |  | No
|  | NA7.4.3- Dynamic Glazing |  | No
|  | NA7.4.4 Clerestories for PAF |  | No
|  | NA7.4.5 Int/Ext Horizontal Slats for PAF |  | No
|  | NA7.4.6 Int/Ext Light Shelves for PAF |  | No
|  | NA7.5.1- Outdoor Air |  | No
|  | NA7.5.2- CV, Single Zone AC/HP's |  | No
|  | NA7.5.3- Air Distribution |  | No
|  | NA7.5.4- Air Economizer Controls |  | No
|  | NA7.5.5- DCV Systems |  | No
|  | NA7.5.6- Supply Variable Flow |  | No
|  | NA7.5.7- Valve Leakage |  | No
|  | NA7.5.8- Supply H2O Temp Reset |  | No
|  | NA7.5.9- Hydronic Variable Flow |  | No
|  | NA7.5.10- Demand Shed (HVAC) |  | No
|  | NA7.5.11- FDD for Package DX |  | No
|  | NA7.5.12- FDD for AHU's/ Zone TU's |  | No
|  | NA7.5.13- DES/DXAC |  | No
|  | NA7.5.14- Thermal Energy Storage |  | No
|  | NA7.5.15- SA Temp Reset |  | No
|  | NA7.5.16- Cond. H2O Temp Reset |  | No
|  | NA7.5.17- Occupied Standby |  | No
|  | NA7.6.1- Daylighting Controls |  | Yes
|  | NA7.6.2- Lighting Shut-Off |  | Yes
|  | NA7.6.3- Lighting Demand Response |  | Yes
|  | NA7.8.2 Motion Sensor |  | Yes
|  | NA7.8.4 Photocontrol |  | Yes
|  | NA7.8.6 Astronomical Time Switch |  | Yes
|  | NA7.8.8 Part-Night Outdoor Lighting |  | Yes
|  | NA7.8.8 Automatic Scheduling |  | Yes
Note on O4: Rebecca Rice: Ben - if checked then compliance in Table C Column 06 says yes. If not checked then compliance in Table C Column 06 says NO.
Note on O20: Rebecca Rice: Ben - use to determine input for 05
Note on L25: 2019 Update: Added some new dropdown choices

## L. Doc & Trg
L. DOCUMENTATION AND TRAINING
Table Instructions: Complete the table below to demonstrate compliance with documentation and training requirements per §120.8(h).
By checking this box, the responsible party1 certifies that a systems manual will be provided to the building owner or representative per §120.8(h)1. | 01
¨
By checking this box, the responsible party1 certifies that a training of the appropriate maintenance staff for each equipement and system will be completed and documented in the commissioning report per §120.8(h)2. Training requirements should be included in the contract document in the specifications. | 02
¨
1 FOOTNOTE: See the signature block on the last page of this compliance document for the responsible party.
Table Tip:
Documentation and training will happen during building turnover to the owner. This table documents that the training will be provided at the appropriate time.

## M. Cx Report
M. COMMISSIONING REPORT
Table Instructions: Complete the table below to demonstrate compliance with commissioning report requirements per §120.8(i).
By checking this box, the responsible party1 certifies that a complete report of commissioning process’ activities undertaken through the design, construction and reporting recommendations for post-construction phases of the building project shall be completed and provided to the owner or owner’s representative. | 01
¨
1 FOOTNOTE: See the signature block on the last page of this compliance document for the responsible party.
Table Tip:
A commissioning report will need to be provided to the building owner at the completion of the commissioning process. This table documents that the report will be provided at the appropriate time.

## N. NRCI
| User input | auto calculated | From another Table | From look up table
N. DECLARATION OF REQUIRED CERTIFICATES OF INSTALLATION
There are no Certificates of Installation applicable to commissioning requirements.

## O. NRCA
| User input | auto calculated | From another Table | From look up table
O. DECLARATION OF REQUIRED CERTIFICATES OF ACCEPTANCE
Although there are no "CXR" Certificates of Acceptance required to document commissioning requirements, Certificates of Acceptance may be used to supplement functional performance testing required by §120.8(g).

## Signature
DOCUMENTATION AUTHOR'S DECLARATION STATEMENT
Documentation Author Name: | Documentation Author Signature:
Company: | Signature Date:
Address: | CEA/ HERS Certification Identification (if applicable):
City/State/Zip: | Phone:
RESPONSIBLE PERSON'S DECLARATION STATEMENT I certify the following under penalty of perjury, under the laws of the State of California: 1. The information provided on this Certificate of Compliance is true and correct. 2. I am eligible under Division 3 of the Business and Professions Code to accept responsibility for the building design or system design identified on this Certificate of Compliance (responsible designer) 3. The energy features and performance specifications, materials, components, and manufactured devices for the building design or system design identified on this Certificate of Compliance conform to the requirements of Title 24, Part 1 and Part 6 of the California Code of Regulations. 4. The building design features or system design features identified on this Certificate of Compliance are consistent with the information provided on other applicable compliance documents, worksheets, calculations, plans and specifications submitted to the enforcement agency for approval with this building permit application. 5. I will ensure that a completed signed copy of this Certificate of Compliance shall be made available with the building permit(s) issued for the building, and made available to the enforcement agency for all applicable inspections. I understand that a completed signed copy of this Certificate of Compliance is required to be included with the documentation the builder provides to the building owner at occupancy.
Responsible Person Name: | Responsible Personal Signature:
Company: | Date Signed:
Address: | License:
City/State/Zip: | Phone:
Tool Tip:
The compliance documentation is not complete until the Documentation Author and Responsible Designer fill out and sign the NRCC-LTI form.
?